## Cover Sheet
ASSIGNMENT 1
DO INITIAL VERSION OF PERSONAL WBS
CSE 6329
Software Metrics and Quality Engineering
Fall, 2015
Name | TASMEEN KAUR KATHURIA
Room | COBA 252 (003)
Points
(/10) Correct Format, including name on top, totals, etc.
(/50) Reasonable list of tasks for each assignment
(/40) Reasonable estimates, actual and earned hours.
(100) Total Assignment Grade
Comments from Grader
1

## Instructions
Instructions for Weekly WBS Entries
Step 1 - Enter hours worked each week
At the end of each week, fill in hours worked on each task, as follows:
(hours may be entered in whole hours, such as 3, or in tenths of an hour, such as 2.3)
For each task:
If you did no work on that task, do nothing.
If you worked on that task during the past week:
Enter total hours worked on the task in the column corresponding to the current week (column V through AJ).
Cell should change color when you enter a non-zero value.
Enter total hours of work remaining on the task in column E:
If the task is complete, enter 0 hours remaining.
The total hours remaining is your best current estimate, which may differ from what was originally anticipated.
Step 2: Check for errors
Review all totals and numbers and make sure everything seems correct.
Make corrections as necessary
Step 3: Record estimated Hours Remaining at End of Current Week
Copy the "total estimated hours remaining" (bottom of column E) to estimated hours remaining cell for current week
Cell will change color
This will update the burndown and burnup charts
Step 4: Update Earned Value
Enter 0 in days earned this week row for the current week (near bottom)
For each task that has completed during the current week:
Find the originally estimated hours for that task and add it to the hours earned this week for the current week
When done, this will update the earned value and the earned value chart

## WBS
|  | PWBS | [9 empty] | Planned Effort | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 | 13.0067 |  | 195.1
Open | 2015 fa | CSE 6329-002 | Schedule | [8 empty] | Cumulative Plan (PV) | 13.0067 | 26.0133 | 39.02 | 52.0267 | 65.0333 | 78.04 | 91.0467 | 104.0533 | 117.06 | 130.0667 | 143.0733 | 156.08 | 169.0867 | 182.0933 | 195.1
In Progress | TASMEEN KAUR KATHURIA | [10 empty] | Estimated Effort Remaining | 195.1 | 182.0933 | 169.0867 | 156.08 | 143.0733 | 130.0667 | 117.06 | 104.0533 | 91.0467 | 78.04 | 65.0333 | 52.0267 | 39.02 | 26.0133 | 13.0067 | 0
Complete | Actual Results |  |  | Estimates |  | WBS | [6 empty] | Actual Hours Worked and Earned
Status | Estimated Hours Remaining | Actual Hours So Far | Actual Completion Week | Estimated Hours of Effort | Planned Completion Week | Task # | [5 empty] | Task Description Week Ending >> | 2015-09-08 | 2015-09-15 | 2015-09-22 | 2015-09-29 | 2015-10-06 | 2015-10-13 | 2015-10-20 | 2015-10-27 | 2015-11-03 | 2015-11-10 | 2015-11-17 | 2015-11-24 | 2015-12-01 | 2015-12-08 | 2015-12-15 | insert new column here | Total Hours Worked
[6 empty] | 10000 | A1 - Develop PWBS
[6 empty] | 11000 |  | Read and Analyze A1 SOW for PWBS | [20 empty] | 0
Complete | 0 | 0.3 |  | 0.3 |  | 11100 |  |  | List tasks to be performed |  |  |  | 2015-09-08: 0.3 |  | 0.3
Complete | 0 | 0.3 |  | 0.3 |  | 11200 |  |  | Break into smaller sub-tasks as required |  |  |  | 2015-09-08: 0.3 |  | 0.3
Complete | 0 | 0.1 |  | 0.3 |  | 11300 |  |  | Modify template to add tasks and correct formulas/coloring |  |  |  | 2015-09-08: 0.1 |  | 0.1
Complete | 0 | 0.1 |  | 0.2 |  | 11400 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  |  | 2015-09-08: 0.1 |  | 0.1
[6 empty] | 12000 |  | Read and Analyze A2 SOW | [20 empty] | 0
Complete | 0 | 1 |  | 1 |  | 12100 |  |  | List tasks to be performed | [19 empty] | 1 | bar: 2015-09-08
Complete | 0 | 1 |  | 1 |  | 12200 |  |  | Break into smaller sub-tasks as required | [19 empty] | 1 | bar: 2015-09-08
Complete | 0 | 1 |  | 1 |  | 12300 |  |  | Modify template to add tasks and correct formulas/coloring | [19 empty] | 1 | bar: 2015-09-08
Complete | 0 | 0.3 |  | 0.5 |  | 12400 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  |  | 2015-09-08: 0.3 |  | 0.3
[6 empty] | 13000 |  | Read and Analyze A3 SOW | [20 empty] | 0
Complete | 0 | 0.5 |  | 0.5 |  | 13100 |  |  | List tasks to be performed |  |  |  | 2015-09-08: 0.5 |  | 0.5
Complete | 0 | 0.6 |  | 1 |  | 13200 |  |  | Break into smaller sub-tasks as required |  |  |  | 2015-09-08: 0.6 |  | 0.6
Complete | 0 | 0.6 |  | 1 |  | 13300 |  |  | Modify template to add tasks and correct formulas/coloring |  |  |  | 2015-09-08: 0.6 |  | 0.6
Complete | 0 | 0.3 |  | 0.5 |  | 13400 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  |  | 2015-09-08: 0.3 |  | 0.3
[6 empty] | 14000 |  | Read and Analyze A4 SOW | [20 empty] | 0
Complete | 0 | 0.4 |  | 0.5 |  | 14100 |  |  | List tasks to be performed |  |  |  | 2015-09-08: 0.4 |  | 0.4
Complete | 0 | 0.3 |  | 0.3 |  | 14200 |  |  | Break into smaller sub-tasks as required |  |  |  | 2015-09-08: 0.3 |  | 0.3
Complete | 0 | 0.5 |  | 0.5 |  | 14300 |  |  | Modify template to add tasks and correct formulas/coloring |  |  |  | 2015-09-08: 0.5 |  | 0.5
Complete | 0 | 0.3 |  | 0.3 |  | 14400 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  |  | 2015-09-08: 0.3 |  | 0.3
Complete | 0 | 0.1 |  | 0.1 |  | 15000 |  | Submit A1 (Draft) |  |  |  |  | 2015-09-08: 0.1 |  | 0.1
Complete | 0 | 1 |  | 1 |  | 16000 |  | Review comments from TA/Instructor and Correct Mistakes | [20 empty] | 1 | bar: 2015-09-15
[6 empty] | 17000 |  | Make Weekly Updates to PWBS | [20 empty] | 0
Complete | 0 | 1 |  | 1 |  | 17100 |  |  | Updates for 9/15 | [19 empty] | 1 | bar: 2015-09-15
Complete | 0 | 1 |  | 1 |  | 17200 |  |  | Updates for 9/22 | [19 empty] | 1 | bar: 2015-09-22
Complete | 0 | 1 |  | 1 |  | 17300 |  |  | Updates for 9/29 | [19 empty] | 1 | bar: 2015-09-29
Complete | 0 | 0.5 |  | 1 |  | 17400 |  |  | Updates for 10/6 |  |  |  | 2015-10-06: 0.5 |  | 0.5
Complete | 0 | 0.6 |  | 1 |  | 17500 |  |  | Updates for 10/13 |  |  |  | 2015-10-13: 0.6 |  | 0.6
Complete | 0 | 0.2 |  | 1 |  | 17600 |  |  | Updates for 10/10 |  |  |  | 2015-10-20: 0.2 |  | 0.2
Complete | 0 | 0.5 |  | 1 |  | 17700 |  |  | Updates for 10/17 |  |  |  | 2015-10-27: 0.5 |  | 0.5
Complete | 0 | 0.4 |  | 1 |  | 17800 |  |  | Updates for 11/3 |  |  |  | 2015-11-03: 0.4 |  | 0.4
Complete | 0 | 0.5 |  | 1 |  | 17900 |  |  | Updates for 11/10 |  |  |  | 2015-11-10: 0.5 |  | 0.5
Complete | 0 | 1 |  | 1 |  | 17910 |  |  | Updates for 11/17 | [19 empty] | 1 | bar: 2015-11-17
Complete | 0 | 0.8 |  | 1 |  | 17920 |  |  | Updates for 11/24 |  |  |  | 2015-11-24: 0.8 |  | 0.8
Complete | 0 | 1 |  | 1 |  | 17930 |  |  | Updates for 12/1 | [19 empty] | 1 | bar: 2015-12-01
Complete | 0 | 0.5 |  | 1 |  | 17940 |  |  | Updates for 12/8 |  |  |  | 2015-12-08: 0.5 |  | 0.5
Complete | 0 | 0.4 |  | 1 |  | 18000 |  |  | Updates for 12/15 |  |  |  | 2015-12-15: 0.4 |  | 0.4
Complete | 0 | 0.1 |  | 1 |  | 20000 |  | Submit Final PWBS |  |  |  |  | 2015-12-15: 0.1 |  | 0.1
[6 empty] | 21000 | A2 | [21 empty] | 0
[6 empty] | 21100 |  | Read A2 SOW | [20 empty] | 0
[6 empty] | 21110 |  |  | For post release quality | [19 empty] | 0
[6 empty] | 21111 |  |  |  | Create Graphh 1 | [18 empty] | 0
Complete | 0 | 1 |  | 1 |  | 21112 |  |  |  |  | Analyze data for 1 year | [17 empty] | 1 | bar: 2015-09-15
Complete | 0 | 0.7 |  | 1 |  | 21113 |  |  |  |  | Analyze data for 1 release |  | 2015-09-15: 0.7 |  | 0.7
Complete | 0 | 1 |  | 1.5 |  | 21120 |  |  |  |  | Record defect data | [17 empty] | 1 | bar: 2015-09-15
[6 empty] | 21121 |  |  |  | Create Graphh 2 | [18 empty] | 0
Complete | 0 | 1 |  | 1.5 |  | 21122 |  |  |  |  | Analyze data for 3 year | [17 empty] | 1 | bar: 2015-09-15
Complete | 0 | 1 |  | 1.5 |  | 21123 |  |  |  |  | Analyze data for 3 release | [17 empty] | 1 | bar: 2015-09-15
Complete | 0 | 1 |  | 1 |  | 21130 |  |  |  |  | Record defect data | [17 empty] | 1 | bar: 2015-09-15
[6 empty] | 21131 |  |  |  | Create Graphh 3 | [18 empty] | 0
Complete | 0 | 1 |  | 1 |  | 21132 |  |  |  |  | Analyze data for 0-12 months | [17 empty] | 1 | bar: 2015-09-15
Complete | 0 | 1 |  | 2 |  | 21133 |  |  |  |  | Analyze data for 3 release | [17 empty] | 1 | bar: 2015-09-15
Complete | 0 | 1 |  | 1.5 |  | 21200 |  |  |  |  | Record defect data | [17 empty] | 1 | bar: 2015-09-15
[6 empty] | 21210 |  |  | For post release quality History | [19 empty] | 0
[6 empty] | 21211 |  |  |  | Create Graphh by month | [18 empty] | 0
Complete | 0 | 0.7 |  | 1 |  | 21212 |  |  |  |  | Analyze data for 3 years |  | 2015-09-22: 0.7 |  | 0.7
Complete | 0 | 0.8 |  | 0.5 |  | 21213 |  |  |  |  | Analyze data for none or 1 or 2 releases |  | 2015-09-22: 0.8 |  | 0.8
Complete | 0 | 0.9 |  | 1 |  | 21220 |  |  |  |  | Record defect data |  | 2015-09-22: 0.9 |  | 0.9
[6 empty] | 21221 |  |  |  | Create Graph by quarter | [18 empty] | 0
Complete | 0 | 1 |  | 1.5 |  | 21222 |  |  |  |  | Analyze data for 3 year | [17 empty] | 1 | bar: 2015-09-22
Complete | 0 | 1 |  | 2 |  | 21223 |  |  |  |  | Analyze data for none to half dozen releases | [17 empty] | 1 | bar: 2015-09-22
Complete | 0 | 1 |  | 1.5 |  | 21230 |  |  |  |  | Record defect data | [17 empty] | 1 | bar: 2015-09-22
[6 empty] | 21231 |  |  |  | Create Graph for an year | [18 empty] | 0
Complete | 0 | 0.6 |  | 0.5 |  | 21232 |  |  |  |  | Analyze data for 1 year |  | 2015-09-29: 0.6 |  | 0.6
Complete | 0 | 0.8 |  | 1 |  | 21300 |  |  |  |  | Record defect data |  | 2015-09-29: 0.8 |  | 0.8
[6 empty] | 21310 |  |  | For post release quality | [19 empty] | 0
[6 empty] | 21311 |  |  |  | Create Graph | [18 empty] | 0
Complete | 0 | 1.3 |  | 1.5 |  | 21400 |  |  |  |  | Analyze 3 years of data by month |  | 2015-09-29: 1.3 |  | 1.3
[6 empty] | 21410 |  |  | Devise own measure | [19 empty] | 0
[6 empty] | 21411 |  |  |  | Create Graph | [18 empty] | 0
Complete | 0 | 1.6 |  | 1 |  | 21412 |  |  |  |  | Analyse class lectures for stastical functions mentioned |  | 2015-10-06: 1.6 |  | 1.6
Complete | 0 | 1.5 |  | 1.5 |  | 22000 |  |  |  |  | Analyze data |  | 2015-10-06: 1.5 |  | 1.5
Complete | 0 | 2.7 |  | 2 |  | 23000 |  |  | Prepare defect analysis report |  |  |  | 2015-10-06: 2.7 |  | 2.7
[6 empty] | 30000 | A3 | [21 empty] | 0
[6 empty] | 31000 |  | Read A3 SOW | [20 empty] | 0
[6 empty] | 31100 |  |  | Own program | [19 empty] | 0
Complete | 0 | 3 |  | 6 |  | 31110 |  |  |  | Develop a program |  |  | 2015-10-20: 3 |  | 3
Complete | 0 | 1 |  | 2 |  | 31120 |  |  |  | Produce a flowchart | [18 empty] | 1 | bar: 2015-10-27
Complete | 0 | 0.3 |  | 1 |  | 31130 |  |  |  | Determine Cyclomatic Complexity |  |  | 2015-10-27: 0.3 |  | 0.3
Complete | 0 | 0.5 |  | 1 |  | 31200 |  |  | Create a word document |  |  |  | 2015-10-27: 0.5 |  | 0.5
Complete | 0 | 0.1 |  | 0.1 |  | 32000 |  | Submit Phase 1 |  |  |  |  | 2015-10-27: 0.1 |  | 0.1
[6 empty] | 33000 |  |  | Programs provided by TA | [19 empty] | 0
[6 empty] | 33100 |  |  |  | Program 1 | [18 empty] | 0
Complete | 0 | 1.5 |  | 1 |  | 33110 |  |  |  |  | Review program for any errors |  | 2015-11-03: 1.5 |  | 1.5
Complete | 0 | 1.7 |  | 1 |  | 33120 |  |  |  |  | Produce a flowgraph of the program |  | 2015-11-03: 1.7 |  | 1.7
Complete | 0 | 0.3 |  | 1 |  | 33130 |  |  |  |  | Comopute cyclomatic complexity of the program |  | 2015-11-03: 0.3 |  | 0.3
Complete | 0 | 0.5 |  | 1 |  | 33140 |  |  |  |  | Edit word file |  | 2015-11-03: 0.5 |  | 0.5
[6 empty] | 33200 |  |  |  | Program 2 | [18 empty] | 0
Complete | 0 | 1 |  | 1 |  | 33210 |  |  |  |  | Review program for any errors | [17 empty] | 1 | bar: 2015-11-03
Complete | 0 | 1 |  | 1 |  | 33220 |  |  |  |  | Produce a flowgraph of the program | [17 empty] | 1 | bar: 2015-11-03
Complete | 0 | 0.3 |  | 1 |  | 33230 |  |  |  |  | Comopute cyclomatic complexity of the program |  | 2015-11-03: 0.3 |  | 0.3
Complete | 0 | 0.5 |  | 1 |  | 33240 |  |  |  |  | Edit word file |  | 2015-11-03: 0.5 |  | 0.5
[6 empty] | 33300 |  |  |  | Program 3 | [18 empty] | 0
Complete | 0 | 1 |  | 1 |  | 33310 |  |  |  |  | Review program for any errors | [17 empty] | 1 | bar: 2015-11-10
Complete | 0 | 0.5 |  | 1 |  | 33320 |  |  |  |  | Produce a flowgraph of the program |  | 2015-11-10: 0.5 |  | 0.5
Complete | 0 | 0.3 |  | 1 |  | 33330 |  |  |  |  | Compute cyclomatic complexity of the program |  | 2015-11-10: 0.3 |  | 0.3
Complete | 0 | 0.5 |  | 1 |  | 33340 |  |  |  |  | Edit word file |  | 2015-11-10: 0.5 |  | 0.5
Complete | 0 | 0.1 |  | 0.1 |  | 34000 |  | Submit phase2 |  |  |  |  | 2015-11-10: 0.1 |  | 0.1
[6 empty] | 40000 | A4 | [21 empty] | 0
[6 empty] | 41000 |  | Read A4 SOW | [20 empty] | 0
[6 empty] | 41100 |  |  | Produce a Swim Lane Diagram | [19 empty] | 0
Complete | 0 | 2.5 |  | 2 |  | 41110 |  |  |  | Read handouts to identify organizations and role they play |  |  | 2015-11-17: 2.5 |  | 2.5
Complete | 0 | 3 |  | 2 |  | 41120 |  |  |  | Determine the order in which things happen and dependencies |  |  | 2015-11-17: 3 |  | 3
Complete | 0 | 3.6 |  | 2 |  | 41130 |  |  |  | Produce swim lane diagram |  |  | 2015-11-17: 3.6 |  | 3.6
Complete | 0 | 1.8 |  | 1 |  | 41140 |  |  |  | Analyze diagram to find out delays and other factors |  |  | 2015-11-17: 1.8 |  | 1.8
Complete | 0 | 3.7 |  | 3 |  | 41200 |  |  | Produce a cause map |  |  |  | 2015-11-24: 3.7 |  | 3.7
[6 empty] | 41300 |  |  | Determine the root causes of customer's problem | [19 empty] | 0
Complete | 0 | 5 |  | 3 |  | 41310 |  |  |  | Use Technique 1 |  |  | 2015-11-24: 5 |  | 5
Complete | 0 | 5 |  | 3 |  | 41320 |  |  |  | Use Technique 2 |  |  | 2015-12-01: 5 |  | 5
Complete | 0 | 5 |  | 1.5 |  | 42000 |  | Prepare the report |  |  |  |  | 2015-12-08: 5 |  | 5
Complete | 0 | 3 |  | 0.1 |  | 43000 |  | Submit A4 |  |  |  |  | 2015-12-15: 3 |  | 3
[6 empty] | 50000 | E1 - Mid-Term Exam | [21 empty] | 0
[6 empty] | 51000 |  | Module 1,2 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 51100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-09-08: 4 |  | 4
Complete | 0 | 3 |  | 3 |  | 51200 |  |  | Read book and make notes |  |  |  | 2015-09-08: 3 |  | 3
[6 empty] | 52000 |  | Module 3,4,5 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 52100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-09-15: 4 |  | 4
Complete | 0 | 3.5 |  | 3 |  | 52200 |  |  | Read book and make notes |  |  |  | 2015-09-15: 3.5 |  | 3.5
[6 empty] | 53000 |  | Module 6,7,8 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 53100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-09-22: 4 |  | 4
Complete | 0 | 3 |  | 3 |  | 53200 |  |  | Read book and make notes |  |  |  | 2015-09-22: 3 |  | 3
[6 empty] | 54000 |  | Module 9,10,11 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 54100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-09-29: 4 |  | 4
Complete | 0 | 3 |  | 3 |  | 54200 |  |  | Read book and make notes |  |  |  | 2015-09-29: 3 |  | 3
[6 empty] | 55000 |  | Module 12,13,14 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 55100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-10-06: 4 |  | 4
Complete | 0 | 2.5 |  | 3 |  | 55200 |  |  | Read book and make notes |  |  |  | 2015-10-06: 2.5 |  | 2.5
[6 empty] | 56000 |  | Module 15,16,17 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 56100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-10-13: 4 |  | 4
Complete | 0 | 3 |  | 3 |  | 56200 |  |  | Read book and make notes |  |  |  | 2015-10-13: 3 |  | 3
[6 empty] | 57000 |  | Module 18,19,20 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 57100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-10-13: 4 |  | 4
Complete | 0 | 3 |  | 3 |  | 57200 |  |  | Read book and make notes |  |  |  | 2015-10-13: 3 |  | 3
Complete | 0 | 7 |  | 6 |  | 52000 |  | Revise notes |  |  |  |  | 2015-10-13: 7 |  | 7
[6 empty] | 50000 | E2-Final Exam | [21 empty] | 0
[6 empty] | 61000 |  | Module 21,22,23 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 61100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-10-20: 4 |  | 4
Complete | 0 | 3 |  | 3 |  | 61200 |  |  | Read book and make notes |  |  |  | 2015-10-20: 3 |  | 3
[6 empty] | 62000 |  | Module 24,25,26 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 62100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-10-27: 4 |  | 4
Complete | 0 | 3.5 |  | 3 |  | 62200 |  |  | Read book and make notes |  |  |  | 2015-10-27: 3.5 |  | 3.5
[6 empty] | 63000 |  | Module 27,28,29 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 63100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-11-03: 4 |  | 4
Complete | 0 | 3 |  | 3 |  | 63200 |  |  | Read book and make notes |  |  |  | 2015-11-03: 3 |  | 3
[6 empty] | 64000 |  | Module 30,31,32 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 64100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-11-10: 4 |  | 4
Complete | 0 | 3 |  | 3 |  | 64200 |  |  | Read book and make notes |  |  |  | 2015-11-10: 3 |  | 3
[6 empty] | 65000 |  | Module 33,34,35 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 65100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-11-17: 4 |  | 4
Complete | 0 | 3 |  | 3 |  | 65200 |  |  | Read book and make notes |  |  |  | 2015-11-24: 3 |  | 3
[6 empty] | 66000 |  | Module 36,37,38 | [20 empty] | 0
Complete | 0 | 4 |  | 4 |  | 66100 |  |  | Go through recorded lectures and slides to make notes |  |  |  | 2015-12-01: 4 |  | 4
Complete | 0 | 3 |  | 3 |  | 66200 |  |  | Read book and make notes |  |  |  | 2015-12-01: 3 |  | 3
Complete | 0 | 6 |  | 6 |  | 62000 |  | Revise notes |  |  |  |  | 2015-12-08: 3; 2015-12-15: 3 |  | 6
Spare Task Rows - For use in Inserting New Tasks and Sub-Tasks
[6 empty] | 90000 | Spare Parent Task - Top Level | [21 empty] | 0
[6 empty] | 99000 |  | Spare Parent Task - Second Level | [20 empty] | 0
[6 empty] | 99900 |  |  | Spare Parent Task - Third Level | [19 empty] | 0
Open | 0 | 0 |  |  |  | 91000 |  | Spare Sub-Task - Second Level | [20 empty] | 0
Open | 0 | 0 |  |  |  | 99100 |  |  | Spare Sub-Task - Third Level | [19 empty] | 0
Open | 0 | 0 |  |  |  | 99910 |  |  |  | Spare Sub-Task - Fourth Level | [18 empty] | 0
Totals >> | 0 | 192 |  | 195.1 |  | Total Actual Hours Worked >> | [6 empty] | 14.7 | 18.2 | 13.4 | 10.7 | 12.8 | 21.6 | 10.2 | 9.9 | 14.2 | 9.9 | 15.9 | 12.5 | 13 | 8.5 | 6.5
| ^ | ^ | ^ | ^ | ^ | Cumulative Actual Hours (AC) >> | [6 empty] | 14.7 | 32.9 | 46.3 | 57 | 69.8 | 91.4 | 101.6 | 111.5 | 125.7 | 135.6 | 151.5 | 164 | 177 | 185.5 | 192 |  | 192
| Total Estimated Hours Remaining | Actual Hours So Far | Actual Completion Week | Total Hours Originally Estimated | Planned Completion Week | Estimated Hours Remaining (copy each week from total in column E) >> | [6 empty] | 184.3 | 156.3 | 140.8 | 129.8 | 117.3 | 96.3 | 82.3 | 70.2 | 54.2 | 42.1 | 30.1 | 20.1 | 9.1 | 2.1 | 0
| (copy to the right at end of each week) | (should match cumulative actual Hours) | (fill in when the task is complete) | (should match cumulative planned effort) | [7 empty] | Week Number >> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Hours Earned This Week >> | [6 empty] | 16.3 | 21 | 15.5 | 11 | 15 | 21 | 14 | 12.1 | 16 | 12.1 | 11 | 10 | 11 | 8.4 | 8.1
[6 empty] | Cumulative Hours Earned (EV) >> | [6 empty] | 16.3 | 37.3 | 52.8 | 63.8 | 78.8 | 99.8 | 113.8 | 125.9 | 141.9 | 154 | 165 | 175 | 186 | 194.4 | 202.5

## GTA Comments
1 | The division of tasks in your WBS is one of the best I have seen for both the classes. It shows that you have taken out time to read and understand all the SOWs.
2 | The Hours Earned this week value (Column U Row 170) is incorrect. It should have been 9.2. Sum up the values in column I for all the completed tasks to get this.
3 | You have missed out the task of completing the WBS under Assignment 1 and submitting the final version of it (After all the updates, task 17940)
4 | You have understood how to use Parent tasks/sub-tasks and where to estimate the effort. Good job on this assignment!